## Sheet1
|  |  | User Story | [5 empty] | Status
Task Id | Name | As a… | I want to be able to… | So that… | Priority | Size | Sprint | To Do | Doing | Done | Added by | Comment
1 | Login | Administrator | login to the system | Create Users | 1 | 10 | 2 |  |  | X | BM | Fixed user id no's to solve creation issue. Access points on DB good.
2 | Login | Administrator | login to the system | Update User Roles | 3 | 3 | 2 |  |  | X | BM
3 | Login | Administrator | login to the system | Deactivate Users | 4 | 2 | 2 |  |  | X | BM
4 | Login | Administrator | login to the system | Activate Users | 2 | 2 | 2 |  |  | X | BM
5 | Login | Administrator | Display User Log | See who access the system. | 5 | 2 | 2 |  |  | X | BM | Created admin component to display ths on admin login.
6 | Journal | User | Create a journal entry. | Be able to record information. | 1 | 9 | 3 |  | X |  | BM
7 | Journal | User | Display a journal entry. | See information. | 2 | 9 | 3 | X |  |  | BM
8 | Journal | User | Update a journal entry. | Verify information. | 3 | 3 | 3 |  | x |  | BM
9 | Journal | User | Deactivate Journal entry. | Remove account no longer in use. | 4 | 2 | 3 |  | x |  | BM
10 | System | Admin | View Account Detail | Make changes to details. | 5 | 2 | 3 |  | x |  | BM
11 | System | Admin | View Event Logs | Understand usage. | 6 | 2 | 3 |  | x |  | BM